## Slide 1: Lecture 3 Project Management (The Classical Approach)
Dr. Hesam Chiniforooshan
se.usc.ac.ir@gmail.com

## Slide 2: Objectives
To explain the main tasks undertaken by project managers
To introduce software project management and to describe its distinctive characteristics
To discuss project planning and the planning process
To show how graphical schedule representations are used by project management
To discuss the notion of risks and the risk management process
To discuss People Management

## Slide 3: Topics covered
Management activities
Project planning
Project scheduling
Risk management
People management

## Slide 4: Topics covered
Management activities
Project planning
Project scheduling
Risk management
People management

## Slide 5: Software project management
Concerned with activities involved in ensuring that software is delivered
  on-time
  on-schedule
  within Budget
  In accordance with the requirements of the organisations developing the software.
Project management is needed because software development is always subject to budget and schedule constraints that are set by the organisation developing the software.

## Slide 6: Management activities
Proposal writing
  To win a contract and carry out the work
  Contains project objectives, initial cost and schedule estimates
  A critical task !! Acquirable through practice and experience
Project planning, scheduling, and costing
  Identifying activities, milestone, deliverables of project
  Drawing a plan toward the project goal
  Estimating resources required to finish the project
Project monitoring and reviews
  Tracking project progress and comparing the actual and planned progress and cost
  Monitoring through formal techniques or informal discussions
  Informal discussions can reveal project problems earlier than formal project review sessions
  Formal review meetings are needed to check the overall project progress
  It is possible that a project review meeting result in the change of original plan or even the cancelation of project
People Management
  Personnel selection and evaluation
  May not be possible to appoint the ideal people to work on a project
    Project budget may not allow for the use of highly-paid staff;
    Staff with the appropriate experience may not be available;
    An organisation may wish to develop employee skills on a software project.
Report writing and presentations
  To both client or contractor organization
  A PM should be able to communicate effectively both orally and in writing

## Slide 7: Management commonalities
These activities are not peculiar to software management.
Many techniques of engineering project management are equally applicable to software project management.
Technically complex engineering systems tend to suffer from the same problems as software systems.

## Slide 8: Software management distinctions
The product is intangible
  In engineering disciplines, e.g. Civil, the product is visible, thus the project progress is visible
  In SE, the product visibility depends on documents to be reviewed
The software development process is not standardised
  In engineering disciplines with long history, the development process is tried and tested
    E.g. in Civil the process of building a bridge or a building is well understood
  However, software processes vary dramatically from one organization to another (or even from one project to another)
Many software projects are 'one-off' projects
  Every Large project is somehow different from previous ones
  Even experienced managers might fail to anticipate problems
  Rapid technological changes can make manager’s experience obsolete
  Lessons learned from previous projects might not be transferable to new projects
Notes: Software project managers do the same kind of job that other engineering managers do – However, there are some distinctions:

## Slide 9: Topics covered
Management activities
Project planning
Project scheduling
Risk management
People management

## Slide 10: Project planning
Probably the most time-consuming project management activity.
Continuous activity from initial concept through to system delivery. Plans must be regularly revised as new information becomes available.
Various different types of plan may be developed to support the main software project plan that is concerned with schedule and budget.

## Slide 11: Types of project plan

## Slide 12: Project planning process
Establish the project constraints
Make initial assessments of the project parameters
Define project milestones and deliverables
while project has not been completed or cancelled loop
Draw up project schedule
Initiate activities according to schedule
Wait ( for a while )
Review project progress
Revise estimates of project parameters
Update the project schedule
Re-negotiate project constraints and deliverables
if ( problems arise ) then
Initiate technical review and possible revision
end if
end loop

## Slide 13: The project plan
The project plan sets out:
  The resources available to the project;
  The work breakdown;
  A schedule for the work.

## Slide 14: Project plan structure
Introduction
  Brief description of project objective and its constraints (budget, time, etc.)
Project organisation
  How the development team is organized, people involved and their role
Risk analysis
  Possible risks, their likelihood, and risk reduction strategies
Hardware and software resource requirements
  Resources needed for the project, and their cost estimates
Work breakdown
  Breaking the project into activities, milestones, and deliverables
Project schedule
  Dependencies between activities, milestones, and staff allocation
Monitoring and reporting mechanisms
  What and when to report about the project

## Slide 15: Activity organization
Activities in a project should be organised to produce tangible outputs for management to judge progress.
  Reports and documents that describe the state of the software being developed
  The rationale behind this definition is that software development is not tangible, so there is need for tangible outputs, which represent its progress
    Do you agree?
Milestones are the recognizable end-point of process activities.
  There should be some formal output, e.g. report
  Milestones should represent the end of a distinct, logical stage in the project
    You cannot have a milestone such as “Code 80% Complete”
Deliverables are project results delivered to customers
  Deliverables are usually milestones, but milestones need not be deliverables
  Milestones might be internal project results, that are used by managers to check the project progress
The waterfall process allows for the straightforward definition of progress milestones.

## Slide 16: Milestones in the RE process
You will see later on that in Agile development the concepts of Activity, Milestone, and Deliverable will severely change

## Slide 17: Topics covered
Management activities
Project planning
Project scheduling
Risk management
People management

## Slide 18: Project scheduling
Split project into tasks and estimate time and resources required to complete each task.
Organize tasks concurrently to make optimal use of workforce.
Minimize task dependencies to avoid delays caused by one task waiting for another to complete.
Dependent on project managers intuition and experience.

## Slide 19: The project scheduling process

## Slide 20: Scheduling problems
Estimating the difficulty of problems and hence the cost of developing a solution is hard.
Productivity is not proportional to the number of people working on a task.
(Brook’s Law) Adding people to a late project makes it later because of communication overheads. It takes some time for the people added to a project to become productive. Brook calls this the "ramp up" time
The unexpected always happens. Always allow contingency in planning.
  Estimate as if nothing will go wrong
    Then increase it to cover anticipated problems (e.g. add 20%)
    Then increase it to cover unanticipated problems (e.g. add 10%)
    Other contingency factors depend on type of project, process parameters (e.g. deadlines, standards, . . .) also quality and experience of your engineers

## Slide 21: Bar charts and activity networks
Graphical notations used to illustrate the project schedule.
Show project breakdown into tasks.
  Tasks should not be too small. They should take about a week or two. ????
Activity charts show task dependencies and the critical path.
Bar charts show schedule against calendar time.

## Slide 22: Task durations and dependencies
Task | Effort (person-days) | Duration (days) | Dependencies
T1 | 15 | 10 | 
T2 | 8 | 15 | 
T3 | 20 | 15 | T1 (M1)
T4 | 5 | 10 | 
T5 | 5 | 10 | T2, T4 (M3)
T6 | 10 | 5 | T1, T2 (M4)
T7 | 25 | 20 | T1 (M1)
T8 | 75 | 25 | T4 (M2)
T9 | 10 | 15 | T3, T6 (M5)
T10 | 20 | 15 | T7, T8 (M6)
T11 | 10 | 10 | T9 (M7)
T12 | 20 | 10 | T10, T11 (M8)

## Slide 23: Activity network

## Slide 24: Activity timeline
Parallel and Sequential activities (due to dependencies)
Critical Path: sequence of dependent activities that define the time required to finish the project (delay of CP activities is critical to the project)
Colored segments show the tolerable delay of the activity or milestone
Notes: M3 is after T1 and T3 are done

## Slide 25: Staff allocation
People don’t have to be assigned to a project at all times – during intervening periods they might be on holydays, working on other projects, attending training course, etc.
Specialists who work on particular tasks (Jim and Mary in the above chart) – this can be cause of scheduling problem – a delay in project and conflict with specialists’ schedule and ripple effect on other projects that the specialist are working
Notes: People don’t have to be assigned to a project at all times – during intervening periods they might be on holydays, working on other projects, attending training course, etc.

## Slide 26: Topics covered
Management activities
Project planning
Project scheduling
Risk management
People management

## Slide 27: Risk management
Risk management is concerned with identifying risks and drawing up plans to minimise their effect on a project.
A risk is a probability that some adverse circumstance will occur
  Project risks affect schedule or resources;
  Product risks affect the quality or performance of the software being developed;
  Business risks affect the organisation developing or procuring the software.

## Slide 28: Software risks
Risk | Affects | Description
Staff turnover | Project | Experienced staff will leave the project before it is finished.
Management change | Project | There will be a change of organizational management with different priorities.
Hardware unavailability | Project | Hardware that is essential for the project will not be delivered on schedule.
Requirements change | Project and product | There will be a larger number of changes to the requirements than anticipated.
Specification delays | Project and product | Specifications of essential interfaces are not available on schedule.
Size underestimate | Project and product | The size of the system has been underestimated.
CASE tool underperformance | Product | CASE tools, which support the project, do not perform as anticipated.
Technology change | Business | The underlying technology on which the system is built is superseded by new technology.
Product competition | Business | A competitive product is marketed before the system is completed.

## Slide 29: The risk management process
Risk identification
  Identify project, product and business risks;
Risk analysis
  Assess the likelihood and consequences of these risks;
Risk planning
  Draw up plans to avoid or minimise the effects of risk;
Risk monitoring
  Monitor the risks throughout the project;

## Slide 30: The risk management process
Notes: The further information you acquire of the project help to revise the risk analysis estimates (of probability and Severity), and consequently the risk plans and monitoring strategy

## Slide 31: Risk identification
Technology risks
  Risks that derive from the software or hardware technologies that are used to develop software
People risks
  Risks that are associate with the people involved in the development team
Organisational risks
  Risks that derive from the organization environment where the software is being developed
Tool Risks
  Risks that derive from the CASE tools and other support software used to develop the system
Requirements risks
  Risks that derive from the changes to the customer requirements and the process of managing the requirements change
Estimation risks
  Risks that derive from the derive from the management estimates of the system characteristics and the resources required to build the system

## Slide 32: Risks and risk types

## Slide 33: Risk analysis
Assess probability and seriousness of each risk.
Probability may be:
  very low (< 10%), low (10–25%), moderate (25–50%), high (50-75%) or very high (>75%).
Risk effects might be:
  Catastrophic, Serious, Tolerable or Insignificant.

## Slide 34: Risk analysis (i)

## Slide 35: Risk analysis (ii)

## Slide 36: Risk planning
Consider each risk and develop a strategy to manage that risk.
  Avoidance strategies
    Following these strategies means the probability that the risk will arise is reduced;
    It does not mean that these strategies certainly prevent the risk
  Minimisation strategies
    Following these strategies means the impact of the risk on the project or product will be reduced;
    For the risk that there is no way to reduce the probability of their occurrence, we can only plan minimisation strategies
  Contingency plans
    Following these strategies means that you are prepared for the worst and have a strategy in place to deal with it

## Slide 37: Risk management strategies (i)

## Slide 38: Risk management strategies (ii)

## Slide 39: Risk monitoring
Assess each identified risks regularly to decide whether or not it is becoming less or more probable.
Also assess whether the effects of the risk have changed.
Each key risk should be discussed at management progress meetings.

## Slide 40: Risk indicators

## Slide 41: Key points
Good project management is essential for project success.
The intangible nature of software causes problems for management.
Managers have diverse roles but their most significant activities are planning, estimating and scheduling.
Planning and estimating are iterative processes which continue throughout the course of a project.

## Slide 42: Key points
A project milestone is a predictable state where a formal report of progress is presented to management.
Project scheduling involves preparing various graphical representations showing project activities, their durations and staffing.
Risk management is concerned with identifying risks which may affect the project and planning to ensure that these risks do not develop into major threats.

## Slide 43: Managing people

## Slide 44: Managing people
People are an organisation’s most important assets.
The tasks of a manager are essentially people-oriented. Unless there is some understanding of people, management will be unsuccessful.
Poor people management is an important contributor to project failure.

## Slide 45: People management factors
Consistency
  Team members should all be treated in a comparable way without favourites or discrimination.
Respect
  Different team members have different skills and these differences should be respected.
Inclusion
  Involve all team members and make sure that people’s views are considered.
Honesty
  You should always be honest about what is going well and what is going badly in a project.

## Slide 46: Motivating people
An important role of a manager is to motivate the people working on a project.
Motivation means organizing the work and the working environment to encourage people to work effectively.
  If people are not motivated, they will not be interested in the work they are doing. They will work slowly, be more likely to make mistakes and will not contribute to the broader goals of the team or the organization.
Motivation is a complex issue but it appears that their are different types of motivation based on:
  Basic needs (e.g. food, sleep, etc.);
  Personal needs (e.g. respect, self-esteem);
  Social needs (e.g. to be accepted as part of a group).

## Slide 47: Human needs hierarchy

## Slide 48: Need satisfaction
In software development groups, basic physiological and safety needs are not an issue.
Social
  Provide communal facilities;
  Allow informal communications e.g. via social networking
Esteem
  Recognition of achievements;
  Appropriate rewards.
Self-realization
  Training - people want to learn more;
  Responsibility.

## Slide 49: Personality types
Task-oriented.
  who are motivated by the work they do
  The motivation for doing the work is the work itself;
Self-oriented.
  who are principally motivated by personal success and recognition
  The work is a means to an end which is the achievement of individual goals - e.g. to get rich, to play tennis, to travel etc.
Interaction-oriented
  who are motivated by the presence and actions of co-workers
  The principal motivation is the presence and actions of co-workers. People go to work because they like to go to work.

## Slide 50: Motivation balance
Individual motivations are made up of elements of each class.
The balance can change depending on personal circumstances and external events.
However, people are not just motivated by personal factors but also by being part of a group and culture.
People go to work because they are motivated by the people that they work with.

## Slide 51: Source
Ivan Sommerville, Software Engineering
  Chapter 22 – Project Management
  Chapter 23 – Project Planning
Roger S. Pressman, Software Engineering: A Practitioner’s Approach
  Chapter 31 – Project management concepts
  Chapter 34 – Project Scheduling
  Chapter 35 – Risk Management